## Roles & Responsibilities
NAME | TEAM | ROLE | Label | RESPONSIBILITIES | Notes
| Full Implementation Team | Core Implementation group | Team
| Lucity Implementation Team | Lucity Lead Implementer | L_PM | Lead Implementer / Project Manager & key contact
| Lucity Implementation Team | Lucity Data Converter | L_Data | Data Conversion, review & approval
| Lucity Implementation Team | Lucity Trainer | L_Train | End-User Training
| Lucity Implementation Support | GIS Expert | L_GIS | GIS Configuration, Consulting & Support
| Lucity Implementation Support | IT Support | L_IT | Installation / Software Support
| Client Core Implementation Team | Client Project Manager | C_PM | Coordinate client resources
| Client Core Implementation Team | CMMS Software Administrator | C_Admin | Future CMMS administrator: dashboards, Security. Etc.
| Client Core Implementation Team | Asset Manager | C_AssetMgr | Asset Manager
| Client Core Implementation Team | GIS Admin / GIS Support | C_GIS | GIS Administrator
| Client Departmental | Departmental Representatives | C_Supr | Departmental Supervisor / decision-maker (C_Sewer, C_Water, C_Streets, etc)
| Client Project Support | IT Administrator | C_IT | IT Administrator: DB Admin, upgrades, etc.
| Client Project Support | Subject Matter Experts (SMEs) | C_SME | Project decision-maker for special interests
| Client Project Support | Client Internal Trainer | C_Train | Client Internal Trainer
| Client Project Support | Director (or representative) | C_Director | Speaks for top-level interests, arbitration & response to resistance
| Client Project Support | CMMS Champion | Champ | Improves project visibility & inclusiveness
Any individual may fulfil several roles & responsibilities. Also, multiple resources may share a role, including outside (consultant) resources.
Shared responsibilities are indicated by '+'. Optional responsible party is indicated by '/'

## Action Item Worksheet
Lucity CMMS Implementation Task Tracker
Update: | 2015-10-06 | Version: | 1.0 |  | Dates
Group | Chore | Task / Issue | Responsibility | % Complete | Effort | Start | Due | Close | Notes
PRE-KICKOFF
Lucity | Project Management | Hand-off from Sales to Implementation | L_Sales & L_PM
Lucity | Project Management | Deliver Preliminary Implementation Materials to Client | L_Sales
SOFTWARE INSTALLATION
IT | Software Installation | Deliver Network Diagram, Lucity Specs | L_PM
IT | Software Installation | Determine & Deliver Installation Component List | L_PM
IT | Software Installation | Identify & Meet Hardware Specifications | C_IT
IT | Software Installation | Deliver Lucity licensing, Admin Login info | L_PM
IT | Software Installation | Core Lucity Installation | C_IT / L_PM
IT | Software Installation | Secondary Lucity Client Installs | C_IT / L_PM
IT | Software Installation | Installer & IT Training | C_IT / L_PM
KICKOFF MEETING - 1ST ON-SITE VISIT
WORKFLOW SETUP CODE BRAINSTORMING (usually at Kickoff)
Lucity | Data Sourcing | Lucity Work Demo & deliver sample WFS | L_PM + C_PM + C_Dept1
Dept1 | Data Sourcing | WorkFlow Setup Code Review & Correction | C_Dept
Dept1 | Data Sourcing | WorkFlow Setup Code final approval | C_Dept
Lucity | Data Conversion | Prepare WFS Codes for load to Lucity | L_PM
Lucity | Data Conversion | Deliver WFS Codes into Lucity | L_PM
DEPARTMENTAL KICKOFF MEETINGS
Dept1 | Department Meeting | Coordinate Department1 Meeting | Team + C_Supr
Dept1 | Data Sourcing | Source Additional Data | Team + C_Supr
Dept1 | Department Meeting | Determine Core Business Processes | Team + C_Supr
Dept1 | Department Meeting | Determine high-level goals (KPIs, reporting needs, etc.) | Team + C_Supr
Dept1 | Data Sourcing | Source PMs (legacy data, manual spreadsheet, etc.)
Dept1 | Software Configuration | PM Training - identify appropriate PM 'mode' (Grouped, etc.)
Dept1 | Software Configuration | Configure PMs (identify Tasks, Frequency, etc.)
Dept1 | Data Conversion | Load PMs to Lucity
SOURCE RESOURCE & CORE DATA
Client | Data Sourcing | Employee List - source data | C_PM
Client | Data Sourcing | Equipment list - source data | C_PM
Client | Data Sourcing | Material list - source data | C_PM
Client | Data Sourcing | Street Name List - source data | C_PM
Client | Data Sourcing | User list (for Security) - source data | C_PM
CONVERT RESOURCE & CORE DATA SOURCES
Lucity | Data Conversion | Employee List - convert data | C_PM / L_Data
Lucity | Data Conversion | Equipment list - convert data | C_PM / L_Data
Lucity | Data Conversion | Material list - convert data | C_PM / L_Data
Lucity | Data Conversion | Street Name List - convert data | C_PM / L_Data
Lucity | Software Configuration | User list (for Security) - enter data into Lucity | C_PM / L_Data
APPROVE RESOURCE DATA CONVERSION
Team | Data Conversion | Employee List - approve converted data | C_PM + L_Data
Team | Data Conversion | Equipment list - approve converted data | C_PM + L_Data
Team | Data Conversion | Material list - approve converted data | C_PM + L_Data
LEGACY DATA CONVERSION
Client | Data Sourcing | Deliver Legacy System Data for conversion | C_PM
Lucity | Data Sourcing | Legacy Data Review & Consult | L_Data / L_PM + C_PM
Lucity | Data Sourcing | Extract Legacy System Data for Client Review & Correction (PMs, codes, etc.) | L_Data
Lucity | Data Review | Lucity Support for Data Corrections - within Scope | L_Data
Dept1 | Data Review | Correct Legacy data in spreadsheet & Deliver for conversion (option) | C_PM / C_Dept
Client | Data Conversion | Field-mapping Legacy Data | C_PM
Lucity | Data Conversion | Convert Legacy data | L_Data
Lucity | Data Conversion | Document Legacy data Conversion (as necessary) | L_Data
Team | Data Conversion | Approval #1 of Legacy data | C_PM + L_Data + L_PM
Lucity | Data Conversion | Re-conversion #1 of Legacy data | C_PM + L_Data
Team | Data Conversion | Final Approval of Legacy data | C_PM + L_Data + L_PM
Lucity | Software Configuration | Deliver Converted Legacy Data into Lucity | L_Data / L_PM
ADDITIONAL DATASOURCE #1 CONVERSION
Client | Data Sourcing | Deliver Datasouce #1 for review | C_PM
Lucity | Data Sourcing | Review Datasouce #1 & Consult | L_Data + C_PM
Lucity | Data Sourcing | Correct Datasouce #1 | C_PM
Lucity | Data Review | Lucity Support for Datasouce #1 Corrections - within Scope | L_Data
Dept1 | Data Review | Convert Datasouce #1 | L_Data
Client | Data Conversion | Document Datasouce #1 Conversion (as necessary) | L_Data
Lucity | Data Conversion | Approval #1 of Datasouce #1 conversion | C_PM + L_Data + L_PM
Lucity | Data Conversion | Re-conversion #1 of Datasouce #1 | C_PM + L_Data
Team | Data Conversion | Final Approval of Datasouce #1 conversion | C_PM + L_Data + L_PM
Lucity | Data Conversion | Deliver Converted Datasouce #1 into Lucity | L_Data / L_PM
GIS - CORE INTEGRATION
GIS | Data Sourcing | GIS - Deliver Feature Classes for integration | C_AssetMgr
GIS | Data Conversion | GIS Audit & field-mapping - identify concerns & areas for improvement | L_GIS + C_GIS
GIS | Data Conversion | Update FC mappings according to audit | C_AssetMgr
GIS | Software Configuration | Complete Feature Class field-mapping | C_AssetMgr
GIS | Data Conversion | Final approval of field mappings | C_GIS + L_GIS
GIS | Software Configuration | Integrate local Client geodatabase | C_GIS + L_GIS
GIS | Software Configuration | deliver linking FC data | C_GIS + L_GIS
Lucity | Data Conversion | deliver Asset Data to Lucity | C_PM + L_PM
GIS - WEB MAP CONFIGURATION
GIS | Software Configuration | Determine Map Requirements (serving all departments) | L_PM / C_PM
GIS | Software Configuration | Create Feature Services | C_GIS
GIS | Software Configuration | Ensure Alias Names are updated | C_GIS + L_GIS
GIS | Software Configuration | Identify Map Services in Admin UI | L_PM / C_GIS
GIS | Software Configuration | Configure Lucity Web Map(s) - select Feature Services | L_PM / C_GIS
SECURITY CONFIGURATION
Client | Security Configuration | Identify Security Groups & Source User list | C_PM
Lucity | Security Configuration | Set 'Typical' (or specified) Security Groups | L_PM
Team | Security Configuration | Review Security Setup / Security Admin Training | L_PM & C_IT
Client | Security Configuration | Import or Enter Users | C_PM / L_PM
Client | Security Configuration | Add additional Users, tweak permissions, etc. | C_IT
WEB DEVELOPMENT - VIEWS & FORMS
Lucity | Web Development | Import Asset & Inspection Views | L_PM
Team | Web Development | Review & Configure Asset & Inspections Views | L_PM & C_Dept1 & C_PM
Lucity | Web Development | Import Work Forms | L_PM
Lucity | Web Development | Customize Basic Work Views & Forms | L_PM
Lucity | Web Development | Copy Work Views for Each Departments | L_PM
Team | Web Development | Review Work Views & Forms with client | L_PM & C_PM & C_Dept1
Team | Web Development | Tweak Views & Forms according to Department Representative | C_PM & C_Dept1
Client | Web Development | Sign-off on Views & Forms | C_PM
Team | Web Development | Web Setup Admin Training - Views & Forms | C_PM & L_PM
WEB DEVELOPMENT - DASHBOARDS
Team | Web Development | Determine relevant business processes | L_PM + C_PM + C_Dept1
Lucity | Web Development | Create Preliminary Dashboard Sample | L_PM
Lucity | Web Development | Design Dashboard based on basic process requirements | L_PM
Team | Web Development | Review & Tweak Dashboards according to specific client needs | L_PM & C_PM & C_Dept1
Client | Web Development | Client Approval of Dashboard setup | C_PM / C_Dept1
Team | Web Development | Web Setup Admin Training - Dashboards | C_PM & L_PM
LUCITY MOBILE
IT | Software Installation | Mobile Component Install & Configure | C_IT
Mobile | Software Configuration | Activate mobile devices
Mobile | Software Configuration | Ensure correct dashboards set up for mobile users
Mobile | Software Configuration | Test & configure map for mobile
PRELIMINARY END-USER TRAINING
Team | End User Training | Develop training plan
Client | End User Training | Identify training facility and resources
Team | End User Training | Determine data plan for training
Team | End User Training | Determine if existing licensing is sufficient for training needs
Team | End User Training | Schedule training classes, resources, and participants
TESTING & ACCEPTANCE
Team | Testing & Acceptance | Prepare Test Plan - client identify what they need to accomplish | C_PM / L_PM
Client | Testing & Acceptance | - Identify basic business process needs | C_PM
Client | Testing & Acceptance | - Identify specialized business process needs (notifications, routing, etc.) | C_PM
Client | Testing & Acceptance | Execute & Report Test Plan Results | C_PM
Client | Testing & Acceptance | Document any setup change requirements | C_PM & Users
Team | Testing & Acceptance | Apply changes per final requirements | C_PM / L_PM
Client | Testing & Acceptance | Final Acceptance | C_PM
DEPARTMENTAL CONFIGURATION APPROVALS (Items not already addressed)
Dept1 | Software Configuration | Work Management Review & Approval | L_PM + C_PM + C_Dept1
Dept1 | Software Configuration | Data Conversion & Preliminary Data Review (where not already done) | L_PM + C_PM + C_Dept1
Dept1 | Software Configuration | Dashboard / Mobile Setup Review & Approval | L_PM + C_PM + C_Dept1
LAUNCH TRAINING
Train | End User Training | Identify training facility and resources | L_Train / C_Train
Train | End User Training | Determine if existing licensing is sufficient for training needs | L_Train / C_Train
Train | End User Training | Schedule training classes, resources, and participants | L_Train / C_Train
Train | End User Training | Train | L_Train / C_Train
GO-LIVE
Team | Go-Live | Final Legacy Data Conversion & Delivery
Team | Go-Live | Replicate Production to Training Environment (or otherwise coordinate)
LAUNCH SUPPORT
Train | End User Training | Identify training resources for internal User support | L_Train / C_Train
Train | End User Training | Identify administrative resources for change requirements | L_Train / C_Train
Train | End User Training | Clear Bogus Training records as necessary | L_PM
FOLLOW-UP TRAINING
Train | End User Training | Follow-up Training 1 | L_Train / C_Train
Train | End User Training | Follow-up Training 2 | L_Train / C_Train
Train | End User Training | Follow-up Training 3 | L_Train / C_Train
PROJECT WRAP-UP
Team | Project Management | Project Wrap-up meeting | L_PM + C_PM
Lucity Tune-Up Visits
Note on C7: Preliminary Client Materials: - 'Initiation letter' - Project Outline - Task Tracker - Software Specifications & Network Diagram - WFS (Work Flow Setup) Samples
Note on C11: - identify whether they want Training and/or Test Clients - deliver list of DBs to be restored
Note on C18: - Identify roles & responsibilities - Source all data - Meet & greet - core implementation team - departmental meetings
Note on C21: May supply Legacy Data Codes for starting point
Note on C30: Typical relevant processes: - Public requests - How are inter-departmental requests passed? - Existing use of paper-copy documents - Manging Work - Assigning Work - Reporting needs - Who "owns" WOs? - Who closes WOs?
Note on C58: discuss options for importing Legacy Data: • Do not load (can revisit Legacy system for history) • Load as-is (historical WO codes will not match ‘new’ Lucity codes going forward, meaning a bit of a compromised system) • Code-mapping (Client creates a mapping of old-codes-to-new so that Legacy System work codes are converted to 'correct' codes in Lucity) • Load historical WO data primarily to comments (avoiding the need to add to code lists entirely)
Note on C59: This optional step allows clients to identify & correct deficiencies in the legacy data before importing it to Lucity.
Note on C60: Lucity can asist in data cleanup subject to the scope of services for the implementation effort.
Note on C74: Lucity can asist in data cleanup subject to the scope of services for the implementation effort.
Note on C94: - Include all Lucity-linked editable assets in Feature Service(s). - Must have edit user. Should be secure if pushed over web. - Ensure Synch field is configured in each GDB. - Identify Read-Only vs. Editable services.
Note on C100: specify what differentiates each group
Note on C103: Ensure Default Rules Groups based on Web Map & Dashboard needs
Note on C119: Best Practice: Include the words 'Tab' / 'Frame', etc. in the component names so that clients become familiar with the naming of Lucity Web elements.
Note on C126: VPN vs. DMZ install & configuration. DMZ demands certificate
Note on C132: includes strategy for final porting of data, reproduction of Production Environment to Training platform, etc.
Note on C160: Plan coordination of client environments according to setup requirements.
Note on C173: Hand-off to Lucity Support & Introduce other Online Resources
Note on C177: After completion of the initial Implementation, it is helpful to occasionally revisit the results with an eye to constant improvement of the business process & CMMS setup within the organization. Lucity Tune-Up visits can be scheduled at any time.

## Notes
Other th8ings to consider (per Jim)
Finer points to consider
· Essential vs. recommended tasks
· Associated deliverables
· Levels of effort (range)
· Sequencing of tasks
· Representative timelines